## Lab Connectivity Requirements
Boards | Console | OOB Management | Regression setup | RPC | Already present in table near Spirent | Spirent Connection
Edgecore AX1 | 172.30.0.47 com1 | Yes | Yes | No (Required) | Yes | Yes (2 ports)
Edgecore AX2 | 172.30.0.47 com3 | Yes | No | No (Required) | Yes | Yes (2 ports)
EdgecoreMX1 | 172.30.162 com2 | Yes | No | No (Required) | Yes | Yes (1 port)
EdgecoreMX2 | 172.30.0.161 com1 | Yes | No | No (Required) | Yes | Yes (1 port)
EdgecoreMX3 | 172.30.0.47 com2 | Yes | No | No (Required) | Yes | No (Required)
EdgecoreMX4 | 172.30.162 com1 | Yes | Yes | No (Required) | Yes | No
UfiSpace AX1 | 172.30.0.161 com3 | Yes | YES | No (Required) | Yes | Yes (1 port)
UfiSpace AX2 | 172.30.0.48 com1 | Yes | No | No (Required) | Yes | Yes (1 port)
Alpha UX1 | 172.30.0.193 com1 | Yes | Yes(To be done) | No (Required) | No (Required) | No (Required)
Alpha UX2 | 172.30.0.194 com1 | Yes | No | No (Required) | No (Required) | No (Required)
Delta UX1 | 172.30.0.195 com1 | Yes | Yes(To be Done) | No (Required) | No (Required) | No (Required)
Delta UX2 | 172.30.0.195 com2 |  | No | No (Required) | No (Required) | No (Required)
Ufispace UX | TBD | Yes | Yes(To be Done) | No (Required) | No (Required) | No (Required)

## Port bringup Status
Boards | Interface type&cable connectivity | Port Bringup status
Edgecore AX | 1 G | DCGSR-1198
| 10 G | Verified
| 25 G | Verified
| 100 G | Verified
EdgecoreMX | 10 G | Verified
| 100 G | Verified
UfiSpace AX | 1G | Not Done
| 10G | Verified
| 25 G | Verified
100 G
Alpha UX | 1G copper
1G Fiber
10G
Delta UX | 1G copper
1G Fiber
10G
Ufispace UX | TBD

## AutoNeg Validation
Port | Link | AutoNeg | Sub test | AX -AXboard | Remarks -AX-AX | UFI-UFI | Remarks(UFI-UFI) | MX-MX | Remarks(MX-MX) | Alpha UX-Alpha UX | Remarks(Alpha-Alpha) | Delta UX-Delta UX | Remarks(Delta-Delta) | UFI UX-UFI UX | Remarks(UFI-UFI)
25G | 25G | Enabled | Auto Neg enabled | PASS |  | PASS
|  |  | Validate traffic | PASS |  | PASS
|  |  | Validate traffic after shut/no shut | PASS |  | PASS
|  |  | Verify same as after MSR | PASS |  | PASS
|  | Disabled | No-Neg enabled | Pass |  | PASS
|  |  | Validate traffic | Pass |  | PASS
|  |  | Validate traffic after shut/no shut | Pass |  | PASS
|  |  | Verify same as after MSR | Pass |  | PASS
| 10G(conncted 10G cable in 25G port) | Enabled | Auto Neg enabled | FAIL | As Nisha suggestion if 25 port (0/19) mention in Config .bcm, port speed as 25G with autoneg.(10G cable).After sending traffic also port speed not changed from 25G to 10G with auto negotation. | Blocked
Validate traffic
|  |  | Validate traffic after shut/no shut |  | BUG ID-DCSGR-1078
Verify same as after MSR
|  | Disabled | No-Neg enabled
Validate traffic
Validate traffic after shut/no shut
Verify same as after MSR
10G | 10G | Enabled | Auto Neg enabled | PASS |  | PASS
|  |  | Validate traffic | PASS |  | PASS
|  |  | Validate traffic after shut/no shut | PASS |  | PASS
|  |  | Verify same as after MSR | PASS |  | PASS
|  | Disabled | No-Neg enabled | PASS |  | PASS
|  |  | Validate traffic | PASS |  | PASS
|  |  | Validate traffic after shut/no shut | PASS |  | PASS
|  |  | Verify same as after MSR | PASS |  | PASS
100G | 100G | Enabled | Auto Neg enabled | Pass |  | Pl confirm if support is there in Ufi for 100G | Pl confirm if support is there in Ufi for 100G
|  |  | Validate traffic | Pass
|  |  | Validate traffic after shut/no shut | Pass
|  |  | Verify same as after MSR | Pass
|  | Disabled | no neg | Pass
|  |  | Validate traffic | Pass
|  |  | Validate traffic after shut/no shut | Pass
|  |  | Verify same as after MSR | Pass
1G (Fibre) | 1G | Enabled | Auto Neg enabled
Validate traffic
Validate traffic after shut/no shut
Verify same as after MSR
|  | Disabled | no neg
Validate traffic
Validate traffic after shut/no shut
Verify same as after MSR
1G (Copper) | 1G | Enabled | Auto Neg enabled
Validate traffic
Validate traffic after shut/no shut
Verify same as after MSR
|  | Disabled | no neg
Validate traffic
Validate traffic after shut/no shut
Verify same as after MSR

## Feature Validation
Boards | Interface type&cable connectivity | LAG | ECFM/ERPS offload | QoS L2, L3, L2VPN, L3VPN | L2 ACL | L3 protocols (OSPF/ISIS/BGP) | L3VPN (VRF interfaces)
Edgecore AX | 1 G | Verified | Verified
| 10 G | Verified | Verified | Verified | Verified | Verified | Verified
| 25 G | Verified | Verified |  | Verified | Verified
| 100 G | Verified | Verified
EdgecoreMX | 10 G | Verified | Verified | FAIL | Verified | Verified | Verified
100 G
UfiSpace AX | 1G
| 10G | Verified | Verified | Verified | Verified | Verified | Verified
| 25 G | Verified | Verified |  | Verified | Verified
100 G
Alpha UX | 1G copper
1G Fiber
| 10G | Verified | Verified |  | Verified | Verified | Verified
Delta UX | 1G copper
1G Fiber
10G
Ufispace UX | TBD